## About
Construction cost tracker
NirmanDost - free tools for people who build. v1 - 10 October 2026
What this is | Your budget for every stage, every rupee actually spent against it, what is still to pay, and how the money moves month by month. The summary turns red the moment a stage goes over its budget.
How to use it | 1. Budget: type the budget for each stage once. Rename the stages to match your contract.
2. Spending: one line per bill or payment. Pick the stage; quantity x rate gives the amount, GST is added, and the balance shows what is still unpaid.
3. Summary: budget, spent, still to pay and variance for each stage, with a chart. Nothing to type.
4. Cash flow: type the year; spending is totalled month by month against the budget, with a running total.
5. Clear the EXAMPLE row before you start. Print: landscape A4.
Sheets in this file | Budget: budget by stage
Spending: the ledger of bills and payments
Summary: budget vs actual by stage, chart
Cash flow: month by month spending and running total
Legend | Sand-coloured cells are yours to type in. Everything else works out by itself. Do not type over a formula.
Free, and more | This file is free. Sign up at nirmandost.in (phone number, one-time code) for the rest of the set, the BOQ calculator and the Site Planner.
Made by NirmanDost, Ahmedabad. It is a working tool, not professional advice: your engineer, your accountant and your contract decide. Report a problem at nirmandost.in.

## Summary
Summary
Budget against what has been spent, stage by stage.
Stage | Budget (Rs) | Spent incl. GST (Rs) | Paid (Rs) | Still to pay (Rs) | Variance (Rs) | % of budget
Approvals and design fees | 0 | 0 | 0 | 0 | 0
Excavation and foundation | 0 | 0 | 0 | 0 | 0
Plinth and DPC | 0 | 0 | 0 | 0 | 0
RCC frame (columns, beams, slabs) | 0 | 43520 | 20000 | 23520 | -43520
Brickwork and lintels | 0 | 0 | 0 | 0 | 0
Electrical | 0 | 0 | 0 | 0 | 0
Plumbing and sanitary | 0 | 0 | 0 | 0 | 0
Waterproofing | 0 | 0 | 0 | 0 | 0
Plaster | 0 | 0 | 0 | 0 | 0
Flooring and tiling | 0 | 0 | 0 | 0 | 0
Doors and windows | 0 | 0 | 0 | 0 | 0
Painting | 0 | 0 | 0 | 0 | 0
Fittings and fixtures | 0 | 0 | 0 | 0 | 0
Site expenses and contingency | 0 | 0 | 0 | 0 | 0
Total | 0 | 43520 | 20000 | 23520 | -43520

## Budget
Budget
Rename the stages if you need to; the other sheets follow these names.
# | Stage | Budget (Rs) | Notes
1 | Approvals and design fees
2 | Excavation and foundation
3 | Plinth and DPC
4 | RCC frame (columns, beams, slabs)
5 | Brickwork and lintels
6 | Electrical
7 | Plumbing and sanitary
8 | Waterproofing
9 | Plaster
10 | Flooring and tiling
11 | Doors and windows
12 | Painting
13 | Fittings and fixtures
14 | Site expenses and contingency
15
16
17
18
19
20
| Total budget | 0

## Spending
Spending
# | Date | Stage | Vendor / paid to | What for | Qty | Unit | Rate (Rs) | Amount (Rs) | GST % | Total (Rs) | Paid (Rs) | Balance (Rs) | Bill no.
1 | 2026-11-03 | RCC frame (columns, beams, slabs) | Palak Traders | OPC 53 cement (EXAMPLE, clear me) | 100 | bag | 340 | 34000 | 28% | 43520 | 20000 | 23520 | PT-201

## Cash flow
Cash flow
Money out, month by month, from the Spending sheet.
Year | 2026
Month | Spent (Rs) | Running total (Rs) | Total budget (Rs)
2026-01-01 | 0 | 0 | 0
2026-02-01 | 0 | 0 | 0
2026-03-01 | 0 | 0 | 0
2026-04-01 | 0 | 0 | 0
2026-05-01 | 0 | 0 | 0
2026-06-01 | 0 | 0 | 0
2026-07-01 | 0 | 0 | 0
2026-08-01 | 0 | 0 | 0
2026-09-01 | 0 | 0 | 0
2026-10-01 | 0 | 0 | 0
2026-11-01 | 43520 | 43520 | 0
2026-12-01 | 0 | 43520 | 0
2027-01-01 | 0 | 43520 | 0
2027-02-01 | 0 | 43520 | 0
2027-03-01 | 0 | 43520 | 0
2027-04-01 | 0 | 43520 | 0
2027-05-01 | 0 | 43520 | 0
2027-06-01 | 0 | 43520 | 0
2027-07-01 | 0 | 43520 | 0
2027-08-01 | 0 | 43520 | 0
2027-09-01 | 0 | 43520 | 0
2027-10-01 | 0 | 43520 | 0
2027-11-01 | 0 | 43520 | 0
2027-12-01 | 0 | 43520 | 0
Two years from January of the year you type. Change the year to move the window.
Formulas:
Spent (Rs) = SUMIFS(Spending!$K5:K404,Spending!$B5:B404,">="&[Month],Spending!$B5:B404,"<="&EOMONTH([Month],0))