## About
House construction Gantt chart
NirmanDost - free tools for people who build. v1 - 10 October 2026
What this is | Every stage of a house on one page: when it starts, how long it takes, what it waits for, and how far along it is. Change a date or a duration and every later bar moves by itself.
How to use it | 1. Setup: type your project start date and site name.
2. Schedule: each row is a stage. Type the days it takes and the row it waits for (the 'After #' column). Leave 'After #' empty for a stage that starts on the project start date. Add a 'Lag' for waiting days such as curing.
3. Type % done as the work moves. The bar fills darker for the finished part; the status turns red when a stage is past its end date and not done.
4. Replace the EXAMPLE durations. They show how a ground-plus-one house might run; your engineer, contractor and weather decide the real ones.
5. Print: landscape A4. The weeks run across the top from your start date.
Sheets in this file | Setup: start date, site name, working note
Schedule: stages, dependencies, days, % done, status, and the weekly bars
Lists: phases and status words used by the drop-downs
Legend | Sand-coloured cells are yours to type in. Everything else works out by itself. Do not type over a formula.
Sources | Stage order follows NirmanDost free guide 4, Footing to finish. Curing and formwork-removal periods are set by IS 456:2000 cl. 11.3 and 13.5 and your engineer's release; the example days are not a standard.
Free, and more | This file is free. Sign up at nirmandost.in (phone number, one-time code) for the rest of the set, the BOQ calculator and the Site Planner.
Made by NirmanDost, Ahmedabad. It is a working tool, not professional advice: your engineer, your accountant and your contract decide. Report a problem at nirmandost.in.

## Schedule
Construction schedule - Type the site name
EXAMPLE durations for a ground-plus-one house. Replace every number with your own. Sand cells are yours to type in.
# | Phase | Stage | After # | Lag | Days | Start | End | % done | Status | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30
1 | Before site | Soil investigation and report |  |  | 10 | 2026-11-02 | 2026-11-11 |  | Not started
2 | Before site | Drawings, structural design and approvals | 1 |  | 30 | 2026-11-12 | 2026-12-11 |  | Not started
3 | Before site | Contract signed, team and materials planned | 2 |  | 7 | 2026-12-12 | 2026-12-18 |  | Not started
4 | Substructure | Setting out and excavation | 3 |  | 5 | 2026-12-19 | 2026-12-23 |  | Not started
5 | Substructure | PCC and footings | 4 |  | 10 | 2026-12-24 | 2027-01-02 |  | Not started
6 | Substructure | Columns to plinth, plinth beam | 5 |  | 10 | 2027-01-03 | 2027-01-12 |  | Not started
7 | Substructure | Anti-termite treatment and DPC | 6 |  | 3 | 2027-01-13 | 2027-01-15 |  | Not started
8 | Frame | Ground floor columns | 7 |  | 8 | 2027-01-16 | 2027-01-23 |  | Not started
9 | Frame | First floor slab and beams (shuttering, steel, pour) | 8 |  | 12 | 2027-01-24 | 2027-02-04 |  | Not started
10 | Frame | Curing and formwork removal (as engineer releases) | 9 |  | 14 | 2027-02-05 | 2027-02-18 |  | Not started
11 | Frame | First floor columns | 10 |  | 8 | 2027-02-19 | 2027-02-26 |  | Not started
12 | Frame | Roof slab and beams | 11 |  | 12 | 2027-02-27 | 2027-03-10 |  | Not started
13 | Frame | Roof slab curing and props removal | 12 |  | 14 | 2027-03-11 | 2027-03-24 |  | Not started
14 | Walls | Brickwork ground floor, lintels | 10 |  | 15 | 2027-02-19 | 2027-03-05 |  | Not started
15 | Walls | Brickwork first floor, lintels | 13 |  | 15 | 2027-03-25 | 2027-04-08 |  | Not started
16 | Services | Electrical conduits and boxes | 15 |  | 7 | 2027-04-09 | 2027-04-15 |  | Not started
17 | Services | Plumbing lines and pressure test | 15 |  | 7 | 2027-04-09 | 2027-04-15 |  | Not started
18 | Finishes | Roof waterproofing | 13 |  | 5 | 2027-03-25 | 2027-03-29 |  | Not started
19 | Finishes | Internal plaster | 17 |  | 15 | 2027-04-16 | 2027-04-30 |  | Not started
20 | Finishes | External plaster | 19 |  | 12 | 2027-05-01 | 2027-05-12 |  | Not started
21 | Finishes | Flooring and wall tiles | 19 |  | 15 | 2027-05-01 | 2027-05-15 |  | Not started
22 | Finishes | Doors, windows and grills | 21 |  | 10 | 2027-05-16 | 2027-05-25 |  | Not started
23 | Finishes | Painting | 22 |  | 15 | 2027-05-26 | 2027-06-09 |  | Not started
24 | Finishes | Electrical fittings, sanitary fittings | 23 |  | 7 | 2027-06-10 | 2027-06-16 |  | Not started
25 | Handover | Snag list, cleaning, handover documents | 24 |  | 5 | 2027-06-17 | 2027-06-21 |  | Not started
26 | Handover | Completion and occupancy certificate | 25 |  | 15 | 2027-06-22 | 2027-07-06 |  | Not started
|  | Project finishes on |  |  |  | 2027-07-06 |  |  |  | Legend: rust = planned, green = done, red = late, sand column = this week. A stage waits for the row number in 'After #'.
|  | Total duration (days) |  |  |  | 247
|  | Stages late today |  |  |  | 0
|  | Overall progress (by days) |  |  |  | 0%

## Setup
Setup
Two inputs. Everything else reads from here.
Project start date | 2026-11-02
Site / project | Type the site name
Durations on the Schedule sheet are calendar days. Sundays and holidays are not skipped; add them as lag if your site stops.

## Lists
Lists
Before site | Not started
Substructure | In progress
Frame | Waiting
Walls | Done
Services
Finishes
Handover