## About
Project tracker
NirmanDost - free tools for people who build. v1 - 10 October 2026
What this is | Every task, every person, every deadline on one sheet, with a dashboard that shows what is late, what is due this week and who is carrying what. Add the site inspections and the decisions you take, so nothing lives only in someone's memory.
How to use it | 1. Tasks: one line per task. Owner, start and due dates, status and % done. Late tasks turn red by themselves.
2. Dashboard: counts by status, late and due-this-week totals, and a chart of open tasks by owner. Nothing to type.
3. Inspections: every check on site (steel before the pour, plumbing pressure test, waterproofing) with who checked and the result.
4. Decisions: what was decided, by whom, and what it changes. A decision log ends most site arguments.
5. Clear the EXAMPLE rows before you start. Print: landscape A4.
Sheets in this file | Tasks: the task list with status and lateness
Dashboard: the summary and chart
Inspections: site checks with results
Decisions: the decision log
Lists: owners, statuses and priorities
Legend | Sand-coloured cells are yours to type in. Everything else works out by itself. Do not type over a formula.
Free, and more | This file is free. Sign up at nirmandost.in (phone number, one-time code) for the rest of the set, the BOQ calculator and the Site Planner.
Made by NirmanDost, Ahmedabad. It is a working tool, not professional advice: your engineer, your accountant and your contract decide. Report a problem at nirmandost.in.

## Dashboard
Dashboard
Updates itself from the Tasks sheet.
Tasks in all | 1
Done | 0
In progress | 1
Waiting | 0
Not started | 0
Late now | 0
Due in the next 7 days | 0
Owner | Open tasks | Late
Owner | 0 | 0
Architect | 0 | 0
Engineer | 0 | 0
Contractor | 1 | 0
Supervisor | 0 | 0
Electrician | 0 | 0
Plumber | 0 | 0
Formulas:
Late = IF([Owner]="","",SUMPRODUCT((Tasks!$D5:D204=[Owner])*(Tasks!$H5:H204<>"Done")*(Tasks!$G5:G204<>"")*(Tasks!$G5:G204<TODAY())))

## Tasks
Tasks
# | Task | Stage / area | Owner | Priority | Start | Due | Status | % done | Done on | Days late | Notes
1 | Order steel for the first floor slab (EXAMPLE, clear me) | Frame | Contractor | High | 2026-11-02 | 2026-11-06 | In progress | 50% |  | 0
Formulas:
Days late = IF(OR([Task]="",[Due]=""),"",IF([Status]="Done",IF([Done on]="","",MAX(0,[Done on]-[Due])),MAX(0,TODAY()-[Due])))

## Lists
Lists
Type your team's names in the Owners column; the drop-downs read from here.
Owners | Status | Priority
Owner | Not started | High
Architect | In progress | Medium
Engineer | Waiting | Low
Contractor | Done
Supervisor
Electrician
Plumber

## Inspections
Site inspections
Check before it is covered: steel before the pour, pipes before the plaster, waterproofing before the tiles.
Date | Stage / element | What was checked | Checked by | Result | Photo / ref | Action needed
2026-11-05 | First floor slab | Bar sizes, spacing, cover blocks and laps against the drawing (EXAMPLE) | Engineer | Pass | IMG_0412

## Decisions
Decision log
What was decided, by whom, and what it changes in cost or time.
Date | Decision | Decided by | Cost change (Rs) | Time change (days) | Recorded by